## Explanation (using Gemini)
Diagram Component/Interaction | Risk Register Sheet(s) | Alignment
Governance (Overarching rules) | Governance | Risks G1-G5 cover policy drift, governance capture, decision latency, role ambiguity, and opaque decisions.
Identity (Actors, entities) | Identity | Risks ID1-ID5 address ambiguous models, weak onboarding, delegation misconfiguration, lifecycle mismanagement, and behavioral opaqueness.
Schemas (Data structure, semantics) | Schemas | Risks S1-S5 cover semantic divergence, schema collisions, under/over-specification, and model drift.
Credentials (Issuance, verification) | Credentials | Risks C1-C5 cover credential misissuance, misbinding, revocation failures, verifier overreach, and protocol downgrade.
Cryptography (Security foundation) | Cryptography | Risks CR1-CR5 cover key leakage, weak entropy, registry poisoning, side-channel leaks, and unbounded registry growth.
AI Agents (Autonomous decision-makers) | AI Agents | Risks AI1-AI5 cover hallucinated decisions, model poisoning, over-autonomy, adversarial inputs, and recursive agent behavior.
Network Managers (Trust graph) | Network Managers | Risks NM1-NM5 cover trust graph manipulation, misissuance by organizations, rCard lifecycle failures, storage misconfiguration, and policy drift across communities.
Human Experience (User interaction) | Human Experience | Risks HX1-HX5 cover low digital literacy, digital exclusion, cognitive overload, consent ambiguity, and trust graph bias.
External (Regulatory, Marketplace) | External | Risks EX1-EX5 cover marketplace malicious inputs, cross-policy incompatibility, regulatory volatility, jurisdiction conflicts, and utility failure.
Systemic/Interactions (Ecosystem failure) | Systemic | Risks SYS1-SYS5 cover cascading failures (a critical risk in any interconnected system), feedback loop polarization, orphan entities, network partitioning, and legacy credential persistence.

## Governance
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
G1 | Policy drift | Decentralised autonomy | Fragmentation | Medium | High | High | Policy harmonisation | Medium | Governing Authority
G2 | Governance capture | Power concentration | Loss of legitimacy | Medium | Critical | Critical | Multi-stakeholder checks | High | Admin Authority
G3 | Decision latency | Slow processes | Operational delays | Medium | Medium | Medium | Time-bound escalation | Low | Gov Council
G4 | Role ambiguity | Weak design | Accountability gaps | Medium | High | High | Clear RACI | Medium | Gov Authority
G5 | Opaque decisions | Poor logging | Regulatory risk | Medium | High | High | Transparent logs | Medium | Admin Authority

## Identity
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
ID1 | Ambiguous identity models | Lack of definitions | Inconsistency | Medium | High | High | Normative profiles | Medium | DTGWG
ID2 | Weak onboarding | Poor KYC/KYB | Fraud risk | High | High | Critical | Strong verification | Medium | Entity Admin
ID3 | Delegation misconfig | Ambiguous policy | Rogue agent actions | High | Critical | Critical | Delegation registry | High | Network Managers
ID4 | Lifecycle mismanagement | Missing deactivation | Ghost identities | Medium | Medium | Medium | Lifecycle governance | Low | Identity Admin
ID5 | Behavioural opaqueness | AI nondeterminism | Misleading decisions | Medium | High | High | Interpretability tooling | Medium | AI Providers

## Schemas
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
S1 | Semantic divergence | Flexible schema | Interop failure | High | High | Critical | Canonical registry | Medium | DTGWG
S2 | Schema collisions | Uncoordinated upgrades | Validation errors | Medium | High | High | Version negotiation | Medium | Standards Body
S3 | Under-specification | Incomplete requirements | Unsafe implementations | Medium | High | High | Mandatory profiles | Medium | Standards Council
S4 | Over-specification | Feature creep | Low adoption | Medium | Medium | Medium | Lean standards | Low | WG
S5 | Model drift | Domain change | Schema invalidity | Medium | Medium | Medium | Periodic reviews | Low | DTGWG

## Network Managers
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
NM1 | Trust graph manipulation | Biased policies | Unfair ranking | Medium | Critical | Critical | Audits | High | Community Managers
NM2 | Misissuance by orgs | Weak checks | Contamination | Medium | High | High | Issuer accreditation | Medium | Credential Board
NM3 | rCard lifecycle failures | Stale relationships | Privacy leakage | Medium | High | High | Lifecycle API | Medium | Personal Manager
NM4 | Storage misconfig | Weak encryption | Breach | Medium | Critical | Critical | HSM storage | Medium | Tech Providers
NM5 | Policy drift across communities | Uncoordinated governance | Interoperability issues | Medium | High | High | Governance sync | Medium | Community Council

## Credentials
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
C1 | Credential misissuance | Human error | Fraud propagation | High | High | Critical | Issuance policy | Medium | Issuer
C2 | Misbinding | Weak binding checks | Wrong entity assignment | Medium | Critical | Critical | Binding proofs | Medium | Issuer
C3 | Revocation failures | Poor registry sync | Stale creds | Medium | High | High | Real-time revocation | Medium | Registry Admin
C4 | Verifier overreach | Poor UX | Data exploitation | Medium | Medium | Medium | Selective disclosure | Low | Verifier
C5 | Protocol downgrade | Adversarial forcing | Weak verification | Low | High | Medium | Protocol enforcement | Low | Verifier

## Cryptography
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
CR1 | Key leakage | Weak storage | Systemic compromise | Medium | Critical | Critical | HSM | Medium | Tech Provider
CR2 | Weak entropy | Bad RNG | Key vulnerability | Low | High | Medium | Entropy validation | Low | Crypto Maintainer
CR3 | Registry poisoning | Malicious writes | Graph corruption | Medium | Critical | Critical | Signed entries | Medium | Registry Admin
CR4 | Side-channel leaks | Hardware flaws | Data inference | Low | High | Medium | Mitigation guards | Low | Infra Provider
CR5 | Unbounded registry growth | Poor pruning | Performance issues | Medium | Medium | Medium | Archiving policies | Low | Registry Admin

## AI Agents
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
AI1 | Hallucinated decisions | LLM unpredictability | False trust actions | Medium | High | High | Policy constraints | Medium | AI Providers
AI2 | Model poisoning | Malicious supply chain | Compromised decisions | Medium | Critical | Critical | Signed models | Medium | Model Provider
AI3 | Over-autonomy | Weak scoping | Unintended actions | Medium | Critical | Critical | Kill switches | Medium | Agent Owner
AI4 | Adversarial inputs | Hostile prompts | Misleading outputs | Medium | High | High | Input sanitisation | Medium | AI Security
AI5 | Recursive agent behaviour | Improper looping | Runaway operations | Low | High | Medium | Rate limiters | Low | Agent Owner

## External
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
EX1 | Marketplace malicious inputs | Unvetted assets | Ecosystem contamination | Medium | High | High | Sandboxing | Medium | Marketplace Admin
EX2 | Cross-policy incompatibility | Governance mismatch | Interop breaks | Medium | Medium | Medium | Policy negotiation | Low | Gov Council
EX3 | Regulatory volatility | Frequent changes | Compliance overhead | Medium | High | High | Legal monitoring | Medium | Compliance
EX4 | Jurisdiction conflicts | Different legal regimes | Enforcement issues | Medium | Medium | Medium | Legal harmonisation | Low | Regulatory Affairs
EX5 | Utility failure | Infra outage | Ecosystem downtime | Low | Critical | High | Redundancy | Low | Infra Provider

## Human Experience
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
HX1 | Low digital literacy | Complex flows | Incorrect usage | High | Medium | High | Assisted flows | Medium | UX Team
HX2 | Digital exclusion | Access barriers | Unequal participation | Medium | High | High | Multi-channel access | Medium | Gov Council
HX3 | Cognitive overload | Poor UX | Drop-offs | Medium | Medium | Medium | Simplified flows | Low | UX Team
HX4 | Consent ambiguity | Bad UI | Uninformed decisions | Medium | High | High | Clear consent screens | Medium | UX + Legal
HX5 | Trust graph bias | Biased data | Discrimination | Medium | High | High | Fairness audits | Medium | Community Managers

## Systemic
Risk ID | Risk Statement | Cause | Consequence | Likelihood | Impact | Inherent Risk | Controls | Residual Risk | Owner
SYS1 | Cascading credential failures | Misissuance | System collapse | Medium | Critical | Critical | Circuit breakers | Medium | Ecosystem Authority
SYS2 | Feedback loop polarisation | Graph reinforcement | Polarisation | Low | High | Medium | Stabilisation policy | Low | Governance Council
SYS3 | Orphan entities | Lifecycle neglect | Ghost graphs | Medium | Medium | Medium | Sunset policy | Low | Identity Admin
SYS4 | Network partitioning | Governance splits | Trust fractures | Low | High | Medium | Interoperability councils | Low | Gov Authority
SYS5 | Legacy credential persistence | Long retention | Attack vectors | Medium | Medium | Medium | Expiry mandates | Low | Credential Board

## Risk to Control Mapping
Risk ID | Risk Name | Control Objective ID | Control Objective Description
G1 | Policy drift | CO1.1 | Governance Coherence & Conformance
G2 | Governance capture | CO1.2 | Anti-Capture & Multi-stakeholder Controls
G3 | Decision latency | CO1.4 | Governance Change Control & Versioning
G4 | Role ambiguity | CO1.1 | Governance Coherence & RACI
G5 | Opaque decisions | CO1.3 | Transparent Adjudication & Auditability
ID1 | Ambiguous identity models | CO3.1 | Issuer/Entity Accreditation Controls
ID2 | Weak onboarding | CO3.1 | Issuer Accreditation & Identity Proofing
ID3 | Delegation misconfiguration | CO4.1 | Delegation Semantics Enforcement
ID4 | Lifecycle mismanagement | CO3.3 | Revocation & Lifecycle Controls
ID5 | Behavioural opaqueness | CO4.2 | Agent Behaviour Controls
S1 | Semantic divergence | CO2.1 | Schema Integrity & Provenance
S2 | Schema collisions | CO2.4 | Registry Access & Coordination
S3 | Under-specification | CO2.1 | Schema Provenance & Integrity
S4 | Over-specification | CO1.4 | Governance Change Control
S5 | Model drift | CO2.1 | Schema Integrity & Updates
NM1 | Trust graph manipulation | CO4.2 | Agent Behaviour Controls
NM2 | Organisational misissuance | CO3.1 | Issuer Accreditation
NM3 | rCard lifecycle failures | CO3.3 | Lifecycle & Revocation Controls
NM4 | Storage misconfiguration | CO2.3 | Cryptographic Hygiene Controls
NM5 | Policy drift across communities | CO1.1 | Governance Coherence
C1 | Credential misissuance | CO3.2 | Credential Quality Controls
C2 | Misbinding | CO3.2 | Credential Binding Controls
C3 | Revocation failures | CO3.3 | Revocation Status & Governance
C4 | Verifier overreach | CO3.4 | Verification Policy Enforcement
C5 | Protocol downgrade | CO3.4 | Verification Protocol Enforcement
CR1 | Key leakage | CO2.3 | Cryptographic Hygiene & HSM Enforcement
CR2 | Weak entropy | CO2.3 | Cryptographic Suitability
CR3 | Registry poisoning | CO2.1 | Registry Integrity
CR4 | Side-channel leaks | CO2.3 | Cryptographic Controls
CR5 | Unbounded registry growth | CO2.2 | Ledger/Registry Continuity Controls
AI1 | Hallucinated decisions | CO4.2 | Agent Behaviour Limits
AI2 | Model poisoning | CO4.3 | AI Supply Chain Integrity
AI3 | Over-autonomy | CO4.4 | Autonomous Decision Limits
AI4 | Adversarial inputs | CO4.2 | Agent Behaviour & Input Validation
AI5 | Recursive agent behaviour | CO4.4 | Autonomy Limits
EX1 | Malicious marketplace inputs | CO4.3 | Agent/Model Supply Chain Controls
EX2 | Cross-policy incompatibility | CO6.1 | Interoperability Controls
EX3 | Regulatory volatility | CO1.1 | Governance Coherence
EX4 | Jurisdiction conflicts | CO1.3 | Transparent Adjudication
EX5 | Utility failure | CO2.2 | Continuity & Redundancy
HX1 | Low digital literacy | CO5.2 | UX Safety Controls
HX2 | Digital exclusion | CO5.2 | UX Access Controls
HX3 | Cognitive overload | CO5.2 | Human Experience Controls
HX4 | Consent ambiguity | CO5.1 | Consent & Transparency Controls
HX5 | Trust graph bias | CO5.3 | Anti-Bias Controls
SYS1 | Cascading failure | CO6.2 | Containment Controls
SYS2 | Feedback-loop polarisation | CO6.3 | Network Health Monitoring
SYS3 | Orphan entities | CO3.3 | Lifecycle Controls
SYS4 | Network partitioning | CO6.1 | Interoperability Controls
SYS5 | Legacy credential persistence | CO3.3 | Lifecycle & Expiry Controls